## Sheet1
Phase 1: Data collection and processing | No. | Description of the task | Responsible | Due date | Status | Indicate what technologies/tools/software were used to solve the problem
| 1 | Collect pictures | Cao Li | Sep. 23 | done | Tools: Camera
| 2 | Compress the pictures | Cao Li | Sep. 23 | done | Software: Pycharm
| 3 | Mark the targets in the pictures | Li Xiang | Sep. 23 | done | Software: Labelimg
| 4 | Use YOLOV5 to train the marked pictures, and generate best.pt files | Li Xiang | Sep. 23 | done | Technologies：yolov5、machine learning
| 5 | Transmit the best.pt files into WTS format and generate them into engine format | Li Xiang | Sep. 23 | done | Tools:
Phase 2: Automatic flight testing and debugging | 6 | Progromming of the spot flight, obstacle avoidance, multi-objects recognization, objects tracing, data analysis and visualization | Yin Zhihao | Sep. 24 |  | Software: Gazebo、Rviz、VSCode Operating system ：Ubuntu 20.04、Robot Operating System（ROS） Technologies：Computer vision（Opencv）
| 7 | Test flights and debug in the simulator | Yin Zhihao | Sep. 24 |  | Software: Gazebo、Prometheus
Phase 3:Developing of the UAV | 8 | 3D printing of the propeller protection and other components | Yin Zhihao | Sep. 25 |  | Software: Solidworks、Creality Print Tools：3D printer
| 9 | UAV assembling and commissioning | Yin Zhihao | Sep. 25 |  | Software: QGroudControl
Phase 4 Real flight with computer vision | 10 | Real spot flight and data visalization | Yin Zhihao | Sep. 26 |  | Tools:Binocular Visual Positioning Camera、 T265、Optical Flow & Laser Range Finder Sensor MTF-01、onboard computers、PX4 Software：NoMachine、Prometheus Technology: Computer vision
| 11 | Real flight of the obstacle avoidance and data visalization | Yin Zhihao | Sep. 26 |  | Tools: depth camera D435i、onboard computers、PX4 Technology: Computer vision Software: NoMachine、Prometheus、Rviz
| 12 | Real flight of the multi-objects recognization and data visalization | Yin Zhihao | Sep. 26
| 13 | Real flight of the objects tracing and data visalization | Yin Zhihao | Sep. 26